## Planning
|  | Game: | PRISON BREAK
|  | Team Members: | Paweł Pudło
Wojciech Szczecina
| Task category | Task name | Task description | Difficulty level [1-3] | Assigned to | Progress [none ¦ in progress ¦ done] | End date
1 | Must have | stages | at last 4 stages | 1 | Wojtek | in progress | 19.05
2 |  | moving by 'WSAD' | implement moving character | 2 | Paweł | in progress | 19.05
3 |  | traps | traps in random spaces on each stage | 1 | Paweł | none | 19.05
4 |  | experience & life points | esp. score increase by picking up food | 2 | Paweł | none | 19.05
5 |  | chest | chests with food and other things somewhere on the maps | 2 | Wojtek | none | 19.05
6 |  | plot | create a story for all game | 1 | Wojtek | in progress | 28.04
1 | Should have | enemies | warders want to catch you | 3 |  |  | 19.05
2
3
4
5
6
1 | Nice to have | shoting | find a gun and shot a warders | 3 |  |  | 19.05
2 |  | limited time | limit time to pass each stage | 2 |  |  | 19.05
3
4
5
6